CLS | Task | #225572 - DA_202112 [QBR] UHS (CORONA)_Q3_2021 | 225577 | DA_202112 [QBR] UHS (CORONA)_Q3_2021 Release / Management | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225499 - Data Analysis_202112 | 225578 | DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 35.00 | 0.00 | 35.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225578 - DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 | 225579 | DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 Analyze / Feedback | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225578 - DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 | 225580 | DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 Verify input data | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225578 - DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 | 225581 | DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 Verify category | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225578 - DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 | 225582 | DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 CS / OP report | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225578 - DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 | 225583 | DA_202112 [QBR] UHS (TEMECULA)_Q3_2021 Release / Management | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225499 - Data Analysis_202112 | 225584 | DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 35.00 | 0.00 | 35.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225584 - DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 | 225585 | DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 Analyze / Feedback | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225584 - DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 | 225586 | DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 Verify input data | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225584 - DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 | 225587 | DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 Verify category | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225584 - DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 | 225588 | DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 CS / OP report | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225584 - DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 | 225589 | DA_202112 [QBR] UHS (INLAND VALLEY REGIONAL MEDICAL CENTER)_Q3_2021 Release / Management | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225499 - Data Analysis_202112 | 225590 | DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 35.00 | 0.00 | 35.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225590 - DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 | 225591 | DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 Analyze / Feedback | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225590 - DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 | 225592 | DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 Verify input data | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225590 - DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 | 225593 | DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 Verify category | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225590 - DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 | 225594 | DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 CS / OP report | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225590 - DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 | 225595 | DA_202112 [QBR] UHS (RANCHO SPRINGS HOSPITAL)_Q3_2021 Release / Management | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225286 - CLS_Scope_202112 | 225596 | Maintenance_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 216.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225597 | Maintain Lib Auto Map SV_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225598 | Maintain_PDF_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 58.25 | -58.25 | 58.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225599 | Maintain_Name_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 4.25 | -4.25 | 4.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225600 | Maintain_CDB_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 137.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225601 | Merged Data Cleansing_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 25.50 | -25.50 | 25.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225602 | Update AC by Noun_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225603 | Sync CM CDB_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225604 | Release CDB To US_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.75 | -0.75 | 0.75 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225605 | Create And Build Cluster Key CLS_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 12.50 | -12.50 | 12.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225606 | Update_data_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 82.75 | -82.75 | 82.75 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225607 | Reset_Change_Original_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 4.50 | -4.50 | 4.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225608 | DE_ProductGroup_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225609 | Get_MSS_data_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:25 PM |  | 0 |  | 2.00 | -2.00 | 2.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225610 | Add_new_item_to_CDB_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225600 - Maintain_CDB_202112 | 225611 | Release_CDB__202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 9.00 | -9.00 | 9.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225612 | Maintain_Category_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225613 | Maintain_HCPCS_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 10.75 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225613 - Maintain_HCPCS_202112 | 225614 | Maintain_HCPCS_202112_Feedback_To_US | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 3.75 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225614 - Maintain_HCPCS_202112_Feedback_To_US | 225615 | Maintain_HCPCS_202112_Merged_Hlib_Prepare | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 1.50 | -1.50 | 1.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225614 - Maintain_HCPCS_202112_Feedback_To_US | 225616 | Maintain_HCPCS_202112_Feedback_To_US_Todo | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225614 - Maintain_HCPCS_202112_Feedback_To_US | 225617 | Maintain_HCPCS_202112_Feedback_To_US_Review | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 2.25 | -2.25 | 2.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225613 - Maintain_HCPCS_202112 | 225618 | Maintain_HCPCS_202112_Merged_Hlib | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 6.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225618 - Maintain_HCPCS_202112_Merged_Hlib | 225619 | Maintain_HCPCS_202112_Merged_Hlib_Todo | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 6.50 | -6.50 | 6.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225618 - Maintain_HCPCS_202112_Merged_Hlib | 225620 | Maintain_HCPCS_202112_Merged_Hlib_Review | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225613 - Maintain_HCPCS_202112 | 225621 | Maintain_HCPCS_202112_Technical Task | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.50 | -0.50 | 0.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225622 | Macro_IR_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 5.25 | -5.25 | 5.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225623 | Maintain_Trademark_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225624 | Maintain_Valid_Item_Lib_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 5.00 | 0.00 | 5.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225625 | Maintain_DE_Item_Lib_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 5.00 | 0.00 | 5.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225626 | Maintain_Attribute_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 10.00 | 0.00 | 10.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225627 | Maintain_Implant_Filter_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 15.00 | 0.50 | 14.50 | 0.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225596 - Maintenance_202112 | 225628 | Maintain UNSPSC | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225286 - CLS_Scope_202112 | 225629 | Defect_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 9.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225629 - Defect_202112 | 225630 | Internal Defect DC_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 5.50 | Linh Pham-Thi-My
CLS | Task | #225630 - Internal Defect DC_202112 | 225900 | [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | New | 3 - Moderate | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 03, 2021 10:06 AM |  | 0 |  | 0.00 | 0.00 | 5.50 | Linh Pham-Thi-My
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225901 | NEW MEPERIA MFR PARENT - "NEW MEPERIA MFR" CÓ VẤN ĐỀ - SAI MFR PARENT, MFR | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 03, 2021 | Dec 31, 2021 | Dec 03, 2021 10:20 AM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225929 | "NOUN/TYPE" CÓ VẤN ĐỀ - INCONSISTENCY | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 09:13 AM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225930 | "NOUN/TYPE" CÓ VẤN ĐỀ - SAI NOUN/TYPE | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 09:34 AM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225960 | "UNSPSC" CÓ VẤN ĐỀ - CÙNG CLUSTER KEY KHÁC UNSPSC | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 02:29 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225961 | "UNSPSC" CÓ VẤN ĐỀ - CÙNG NOUN TYPE KHÁC UNSPSC | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 02:52 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225962 | UOM/QOE CÓ VẤN ĐỀ - SAI UOM/QOE | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 03:28 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225963 | TRADEMARK CÓ VẤN ĐỀ - CÙNG CLUSTER KEY KHÁC TRADEMARK | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 03:28 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225964 | TRADEMARK CÓ VẤN ĐỀ - SAI TRADEMARK | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 03:29 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225965 | TRADEMARK CÓ VẤN ĐỀ - TRADEMARK, MODEL, STYLE LẪN LỘN | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 03:30 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225966 | TRADEMARK CÓ VẤN ĐỀ - CÙNG TRADEMARK KHÁC MFR | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 03:31 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225967 | "ATTRIBUTE" CÓ VẤN ĐỀ - INCONSISTENCY | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 03:55 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225968 | "ATTRIBUTE" - CÓ VẤN ĐỀ LOGIC | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 04:05 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225969 | COMPOSITION CÓ VẤN ĐỀ - SAI COMPOSITION | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 04:19 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225970 | COMPOSITION CÓ VẤN ĐỀ - SAI FORMAT | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 04:19 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225971 | COMPOSITION CÓ VẤN ĐỀ - INCONSISTENCY | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 04:20 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225973 | "ATTRIBUTE" - DUPLICATE WORD | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 04:48 PM |  | 0 |  | 5.50 | -5.50 | 5.50 | Khanh Nguyen-Le-Cong
CLS | Defect / Bug | #225900 - [DEFECT-CLEANSING] DC_202112 Monthly_10_P2&3 | 225974 | ATTRIBUTE - CÙNG CLUSTER KEY KHÁC MFD | Resolved |  | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 06, 2021 04:59 PM |  | 0 |  | 0.00 | 0.00 | 0.00 | Khanh Nguyen-Le-Cong
CLS | Task | #225629 - Defect_202112 | 225631 | Internal Defect DS_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225631 - Internal Defect DS_202112 | 225632 | Internal Defect Name Normalization_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225631 - Internal Defect DS_202112 | 225633 | Internal Defect T120N_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225631 - Internal Defect DS_202112 | 225634 | Internal Defect Centralized Images_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225629 - Defect_202112 | 225635 | Internal Defect DA_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225629 - Defect_202112 | 225636 | External Defect DC_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 02, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 3.75 | Dung Nguyen-Trung
CLS | Defect / Bug | #225636 - External Defect DC_202112 | 225860 | [Ext. Defect 202112] [issue mgmt.] [PRODUCTION] Issue Mgmt Dec 02, 2021 | Resolved |  | 4. Medium | CLS_Milestone_Unknown | Dec 02, 2021 | Dec 31, 2021 | Dec 02, 2021 01:27 PM |  | 0 |  | 0.50 | -0.50 | 0.50 | Dung Nguyen-Trung
CLS | Defect / Bug | #225636 - External Defect DC_202112 | 225928 | [Ext. Defect 202112] [issue mgmt.] HIGH PRIORITY - ORG ITEM 4356 | Resolved |  | 4. Medium | CLS_Milestone_Unknown | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 08:45 AM |  | 0 |  | 0.75 | -0.75 | 0.75 | Dung Nguyen-Trung
CLS | Defect / Bug | #225636 - External Defect DC_202112 | 225972 | [Ext. Defect 202112] [issue mgmt.] [PRODUCTION] Issue Mgmt Dec 06, 2021 | Resolved |  | 4. Medium | CLS_Milestone_Unknown | Dec 06, 2021 | Dec 31, 2021 | Dec 06, 2021 04:26 PM |  | 0 |  | 1.75 | -1.75 | 1.75 | Dung Nguyen-Trung
CLS | Defect / Bug | #225636 - External Defect DC_202112 | 225988 | [Ext. Defect 202112] [issue mgmt.] [PRODUCTION] Issue Mgmt Dec 07, 2021 | Resolved |  | 4. Medium | CLS_Milestone_Unknown | Dec 07, 2021 | Dec 31, 2021 | Dec 07, 2021 04:15 PM |  | 0 |  | 0.25 | -0.25 | 0.25 | Dung Nguyen-Trung
CLS | Defect / Bug | #225636 - External Defect DC_202112 | 226009 | [Ext. Defect 202112] [issue mgmt.] [PRODUCTION] Issue Mgmt Dec 08, 2021 | Resolved |  | 4. Medium | CLS_Milestone_Unknown | Dec 08, 2021 | Dec 31, 2021 | Dec 08, 2021 05:31 PM |  | 0 |  | 0.50 | -0.50 | 0.50 | Dung Nguyen-Trung
CLS | Task | #225629 - Defect_202112 | 225637 | External Defect DA_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225629 - Defect_202112 | 225638 | External Defect DS_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225286 - CLS_Scope_202112 | 225639 | Others_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 74.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225639 - Others_202112 | 225640 | Data review_CM changes weekly_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 1.00 | -1.00 | 74.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225640 - Data review_CM changes weekly_202112 | 225641 | Data review_CM changes weekly_202112 HCPCS | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225640 - Data review_CM changes weekly_202112 | 225642 | Data review_CM changes weekly_202112 Others | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 65.00 | -65.00 | 65.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225640 - Data review_CM changes weekly_202112 | 225643 | Data review_CM changes weekly_202112 Technical Task | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 8.25 | -8.25 | 8.25 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225286 - CLS_Scope_202112 | 225644 | Outsource_202112 | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 53.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #225644 - Outsource_202112 | 225792 | Crawling for Atalink_202112 | New | 3 - Moderate | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 02, 2021 09:14 AM |  | 0 |  | 0.00 | 0.00 | 53.50 | Linh Pham-Thi-My
CLS | Task | #225792 - Crawling for Atalink_202112 | 225849 | Crawling for Atalink_202112 Meeting | New | 3 - Moderate | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 02, 2021 09:20 AM |  | 0 |  | 0.00 | 0.00 | 0.00 | Linh Pham-Thi-My
CLS | Task | #225792 - Crawling for Atalink_202112 | 225850 | Crawling for Atalink_202112 Analyze and Estimate | New | 3 - Moderate | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 02, 2021 09:20 AM |  | 0 |  | 0.00 | 0.00 | 0.00 | Linh Pham-Thi-My
CLS | Task | #225792 - Crawling for Atalink_202112 | 225851 | Crawling for Atalink_202112 To Do | New | 3 - Moderate | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 02, 2021 09:21 AM |  | 0 |  | 46.00 | -46.00 | 46.00 | Linh Pham-Thi-My
CLS | Task | #225792 - Crawling for Atalink_202112 | 225852 | Crawling for Atalink_202112 Review | New | 3 - Moderate | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 02, 2021 09:21 AM |  | 0 |  | 6.75 | -6.75 | 6.75 | Linh Pham-Thi-My
CLS | Task | #225792 - Crawling for Atalink_202112 | 225854 | Crawling for Atalink_202112 Management | New | 3 - Moderate | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 02, 2021 09:22 AM |  | 0 |  | 0.75 | -0.75 | 0.75 | Linh Pham-Thi-My
CLS | Task |  | 225645 | Crawling for Atalink_202112 Meeting | New | 1 - Very Easy | 4. Medium | CLS_Milestone_202112 | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Linh Pham-Thi-My
CLS | Task |  | 225646 | Outsource_202112 Analyze and Estimate | New | 1 - Very Easy | 4. Medium |  | Dec 01, 2021 | Dec 31, 2021 | Dec 01, 2021 06:26 PM |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | Linh Pham-Thi-My
CLS | Task | #89910 - F3. Engineering | 172502 | Task_Backlog_CDB | Closed | 3 - Moderate | 4. Medium |  | Aug 01, 2020 | Dec 31, 2022 | Aug 25, 2020 11:28 AM |  | 0 |  | 0.00 | 0.00 | 0.00 | Linh Pham-Thi-My
CLS | Task | #206194 - F3.5. Research & Development | 216947 | R&D_Crawling | New | 3 - Moderate | 4. Medium |  | Oct 21, 2021 | Dec 31, 2023 | Oct 21, 2021 03:01 PM |  | 0 |  | 4.00 | -4.00 | 4.00 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #206194 - F3.5. Research & Development | 216948 | R&D_Data Analysis | New | 3 - Moderate | 4. Medium |  | Oct 21, 2021 | Dec 31, 2023 | Oct 21, 2021 03:02 PM |  | 0 |  | 5.50 | -5.50 | 5.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task |  | 89903 | F2. Management | New | 3 - Moderate | 4. Medium |  | Aug 01, 2016 | Dec 31, 2026 | Jul 03, 2017 02:39 PM |  | 33 |  | 26.25 | -26.25 | 52,172.31 | Tuyen Ho-Thi-Kim | F2. Management
CLS | Task | #89903 - F2. Management | 89908 | F2.4. Monitor and Control Project | New | 1 - Very Easy | 4. Medium |  | Aug 01, 2016 | Dec 31, 2026 | Jul 03, 2017 02:49 PM |  | 56 | 2,000.00 | 2,043.25 | -43.25 | 7,526.00 | Trang Pham-Tran-Minh | F2.4. Monitor and Control Project
CLS | Task | #89908 - F2.4. Monitor and Control Project | 64688 | Monitor and Control Risk/Issue | New | 1 - Very Easy | 4. Medium |  | Aug 16, 2016 | Dec 31, 2026 | Aug 02, 2016 04:02 PM |  | 91 | 0.00 | 104.00 | -104.00 | 237.25 | Trang Pham-Tran-Minh | F2.4. Monitor and Control Project
CLS | Task | #64688 - Monitor and Control Risk/Issue | 164821 | Issue liên quan việc map hình theo Noun Type | Closed | 3 - Moderate | 4. Medium | CLS_Milestone_Unknown | Jun 10, 2020 | Dec 31, 2026 | Jun 10, 2020 03:52 PM |  | 100 |  | 0.00 | 0.00 | 0.00 | Tuyen Ho-Thi-Kim
CLS | Task | #89910 - F3. Engineering | 89915 | F3.2. Develop Product Scope | Re-opened | 1 - Very Easy | 4. Medium |  | Jan 31, 2016 | Dec 31, 2026 | Jul 03, 2017 03:08 PM |  | 99 | 0.00 | 0.00 | 0.00 | 169,952.45 | Tam Le-Minh | F3.2. Develop Product Scope
CLS | Task | #89915 - F3.2. Develop Product Scope | 160480 | CLS_Scope_202005 | Closed | 3 - Moderate | 4. Medium | CLS_Milestone_202005 | May 01, 2020 | Dec 31, 2026 | May 05, 2020 11:46 AM |  | 100 |  | 0.00 | 0.00 | 2,387.50 | Linh Pham-Thi-My | F3.2. Develop Product Scope
CLS | Task | #160480 - CLS_Scope_202005 | 160712 | Defect_202005 | Closed | 1 - Very Easy | 4. Medium | CLS_Milestone_202005 | May 05, 2020 | Dec 31, 2026 | May 05, 2020 11:53 AM |  | 100 | 0.00 | 0.00 | 0.00 | 1.25 | Linh Pham-Thi-My
CLS | Task | #160712 - Defect_202005 | 160716 | External Defect DC_202005 | Closed | 1 - Very Easy | 4. Medium | CLS_Milestone_202005 | May 05, 2020 | Dec 31, 2026 | May 05, 2020 11:53 AM |  | 100 |  | 0.00 | 0.00 | 1.25 | Linh Pham-Thi-My
CLS | Defect / Bug | #160716 - External Defect DC_202005 | 160721 | [Ext. Defect 202005] [issue mgmt.] "Fwd: Maricopa - Review Item Picture" | Closed |  | 4. Medium | CLS_Milestone_Unknown | May 05, 2020 | Dec 31, 2026 | May 05, 2020 12:29 PM |  | 100 |  | 0.50 | -0.50 | 0.50 | Linh Pham-Thi-My
CLS | Task | #89915 - F3.2. Develop Product Scope | 200976 | CLS_Scope_202106 | Closed | 3 - Moderate | 4. Medium | CLS_Milestone_202106 | Jun 01, 2021 | Dec 31, 2026 | Jun 01, 2021 03:48 PM |  | 100 |  | 0.00 | 0.00 | 2,485.50 | Yen Nguyen-Thien | F3.2. Develop Product Scope
CLS | Task | #200976 - CLS_Scope_202106 | 201126 | Defect_202106 | Closed | 1 - Very Easy | 4. Medium | CLS_Milestone_202106 | Jun 01, 2021 | Dec 31, 2026 | Jun 01, 2021 03:54 PM |  | 100 | 0.00 | 0.00 | 0.00 | 10.25 | Yen Nguyen-Thien
CLS | Task | #201126 - Defect_202106 | 201129 | External Defect DC_202106 | Closed | 1 - Very Easy | 4. Medium | CLS_Milestone_202106 | Jun 02, 2021 | Dec 31, 2026 | Jun 01, 2021 03:54 PM |  | 100 | 0.00 | 0.00 | 0.00 | 5.50 | Yen Nguyen-Thien
CLS | Defect / Bug | #201129 - External Defect DC_202106 | 202713 | [Ext. Defect 202106] [issue mgmt.] [PRODUCTION] Issue Export Jun 05, 2021 | Closed |  | 4. Medium | CLS_Milestone_Unknown | Jun 07, 2021 | Dec 31, 2026 | Jun 07, 2021 04:01 PM |  | 100 |  | 0.50 | -0.50 | 0.50 | Yen Nguyen-Thien
CLS | Defect / Bug | #201129 - External Defect DC_202106 | 202727 | [Ext. Defect 202106] [issue mgmt.] [PRODUCTION] Issue Export Jun 05, 2021 | Closed |  | 4. Medium | CLS_Milestone_Unknown | Jun 09, 2021 | Dec 31, 2026 | Jun 09, 2021 04:15 PM |  | 100 |  | 0.50 | -0.50 | 0.50 | Yen Nguyen-Thien
CLS | Task |  | 89910 | F3. Engineering | Re-opened | 3 - Moderate | 4. Medium |  | Jan 31, 2016 | Jul 31, 2036 | Jul 03, 2017 03:06 PM |  | 82 |  | 0.00 | 0.00 | 191,001.70 | Tam Le-Minh | F3. Engineering
CLS | Task | #89910 - F3. Engineering | 206194 | F3.5. Research & Development | New | 1 - Very Easy | 4. Medium |  | Jul 01, 2021 | Jul 31, 2036 | Jul 26, 2021 03:31 PM |  | 0 | 0.00 | 0.00 | 0.00 | 47.75 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #206194 - F3.5. Research & Development | 206195 | R&D_Create WBS | New | 1 - Very Easy | 4. Medium |  | Jul 01, 2021 | Jul 31, 2036 | Jul 26, 2021 03:31 PM |  | 0 | 0.00 | 7.50 | -7.50 | 7.50 | Ngan Nguyen-Thi-Ngoc
CLS | Task | #206194 - F3.5. Research & Development | 206196 | R&D_Meeting | New | 1 - Very Easy | 4. Medium |  | Jul 01, 2021 | Jul 31, 2036 | Jul 26, 2021 03:31 PM |  | 0 | 0.00 | 30.75 | -30.75 | 30.75 | Ngan Nguyen-Thi-Ngoc
CLS | Defect / Bug | #64688 - Monitor and Control Risk/Issue | 179622 | Issue report DA có vấn đề, cần phải process và gửi lại report cho phía khách hàng | Closed |  | 3. High | CLS_Milestone_202010 | Oct 27, 2020 | Oct 31, 2020 | Oct 27, 2020 05:32 PM |  | 100 |  | 0.00 | 0.00 | 0.00 | Nhan Duong-Thi-Ai
CLS | Task | #214949 - Defect_202110 | 222110 | External Defect DA_202110 | Closed | 3 - Moderate | 2. Urgent | CLS_Milestone_202110 | Oct 11, 2021 | Oct 31, 2021 | Nov 05, 2021 11:33 AM |  | 100 |  | 0.00 | 0.00 | 0.00 | Ngan Nguyen-Thi-Ngoc
CLS | Defect / Bug | #222110 - External Defect DA_202110 | 222111 | Ext. Bug - Sales Assessment của Commonspirit hiển thị sai thông tin FDA cost và bar chart IM/PO items | Closed |  | 2. Urgent | CLS_Milestone_Unknown | Oct 11, 2021 | Oct 31, 2021 | Nov 05, 2021 11:36 AM |  | 100 |  | 0.00 | 0.00 | 0.00 | Minh Trinh-Ngo-Anh
Total: | [13 empty] | 208,713.98 | 243,048.76 | -34,334.78